01734-094_-#6212 – University Park Village

Ft Worth, TX- Bid Notes

Project Information: GC responsible for ALL information in these bid notes.

Box Link to Bid Folder: https://sbuxsd.box.com/s/pncncii5d22lu8d02v8csil8sotsqpvd

- Project Address: 1620 S University DR, Fort Worth, TX 76107

- CPN: 01734-094

- STORE NUMBER: 6212

- Documents: Drawings Dated 6/17/2025

- Landlord Work: see Refer to LL Minimal work email in bid folder.

-We are responsible for New GT and Fire Sprinkler system (I have already provided CAD files to LL required sub for design and cost)

-HVAC units procured by SBUX

- BID DUE DATE: Day 11/07/2025 – EOD

- SF: Expansion to 2,652SF

- RTU: 3 RTU’s – SBUX Procured

- Anticipated start of Deliveries: 10/15/2025

- Delivery of Possession Walk: NA

- Anticipated Construction Start:   Monday – 2/23/26 (Planned)

- Anticipated Construction Completion (100%): 6/17/26

- Punch Walk Date: 06/18/2026 (Store Must be 100%) less punch items identified by Starbucks.

- Ops Presentation/Turnover: 06/25/2026 (If the store is not complete by this date Starbucks may enforce Paragraph 12.1 of contract concerning delays)

- Store Open: Monday, 03/16/2026

- Bid Form: Please use Compass. ONLY use categories in the Compass/Budget Tool bid form unless discussed with PM. If we have missed a field, we will inform all bidders, so we compare like for like. (I have uploaded Line items into Bid please

- Exclusions & Qualifications: GC Must identify any exclusions or qualifications of their bid in notes on bid submission and a separate email addressed to Starbucks Project Manager and Project Specialist on day of bid submission. If something is unclear for either the GC or Subcontractor, an RFI must be submitted before the bid is submitted.

- Schedule: Provide a proposed schedule even if it is not different from above. Schedule shall be submitted in a separate email addressed to Starbucks Project Manager and Project Specialist on day of bid submission.  Please also note start and end dates in bid response in Compass.

- Staffing Requirements: GC MUST have a representative from your company onsite with any subs. A superintendent or other qualified representative MUST be onsite at DOP, punch walk, turnover, and opening day. GC representative must remove Coming Soon Banner and Install Now Open Banner and Flags(s). Open Space capture must be performed at DOP, at least every 3 days during construction, after punch walk and the day of turnover.

- Starbucks Provided Material, Delivery, Inventory and Storage– GC is to provide storage for Starbucks procured items.  GC is required to inventory incoming deliveries to check for damage and ensure the packing slip matches the amount delivered.  Any discrepancies should be reported to the PM & PS within 24 hrs. GC to provide a missing items list 2 weeks prior to construction start.

- Finished Photos: GCs are responsible for final photos. -GCs should utilize HomeJab and coordinate directly with Home Jab. HomeJab Photos: sales@homejab.com or (855)-226-830.  Please include the price of the photo session in your bid.

- Change Orders: Change orders must be approved by PM in writing prior to work being performed.  Change order log must be submitted to PM for alignment and submitted in Compass as they happen and cannot be held until the end of the project. GC should ensure full understanding of the permitted plans, bid notes and LLWL before submitting bid.  RFI’s should be submitted for anything that is not clear before the bid is submitted.

- Permit Reimbursement over allowance will be made through Work Task Contract upon request. Please include a minimum of $3500 for permit in your bid.

- GC is responsible for ensuring ALL permits (including the retail operating permit & health permit if required), inspections, fees, and utility set-up/hook-up requirements are fulfilled or coordinated.  GC is to cover the cost of utilities during construction and should have all accounts switched to their name when construction begins. Responsibility also includes providing meter information to Starbucks PS or filling out and submitting the utility meter submission form via email.

- GC may be asked to share bids from individual trades. GCs are encouraged to get multiple bids from MEP subs specifically. GC’s will also be required to supply a sub-contractor list, on the required Starbucks form, at the time of contract signing.

- GC is responsible for ALL FEES associated with LL Contractor Rules and Regulations. Please see Contractor Rules and Regulations doc in Bid folder and account for in bid.

Specific Requests:

  - Include one (1) 6’ Fiberglass Ladder, one (1) security cable 25-30ft long (see example below), two (2) (combination padlock) with changeable code. (These were examples, PMs may add or remove other items as well)

  - Include a key box see below) that will hold all keys(labeled). See the example below. The only keys handed over to SM at turnover will be one front door key and one key box key. All other keys must be labeled and placed in the key box by GC.

PLEASE NOTE standards and requirements are being enforced and reviewed at Starbucks. Please check current requirements.  Please ask questions Starbucks designers and PMs do make mistakes too; please submit any RFI’s to PM from within Compass

Project overview:

Tenant Expansion

At Construction start - GC is responsible for verifying all utilities, measurements, and penetrations as depicted on drawings (both TI & LL) and verify measurements against casework shop drawings and FF&E plans. Any variation or discrepancies should be reported to PM immediately. Slab pour back, and undergrounds are by SBUX GC and GC is responsible for verifying grade is correct at possession..

Specific alterations to Bid Set for Store 87890 – LL will not provide the following items and they will be installed at the cost of GC, please be sure to include these in your bid:

Back flow Preventor Plans have by LL that is not correct

Grease interceptor GB250 Plans have by LL that is not correct .

Fire sprinkler replacement as the current is 30yrs old

LL required subs and Fees

SBUX is providing RTUs.  GC to install and price ductwork and exhaust fans as shown in plans. Do not include test & balance costs as these will be provided by Melink and SBUX will cover costs directly. GC will be responsible for the coordination of the initial visit with Melink, and any corrections or revisits required upon receipt of report, will be at GC cost.

GC must use LL roofer for all roof penetrations as outlined in LLWL. Please include a $5000 allowance to pay LL roofer per site specific LLWL. A copy of the LLWL is located in the Bid Folder.

If not otherwise noted, GC will be responsible for installing all SBUX provided equipment and systems, including refrigerators and freezers, brewers, data rack, etc.  If you have specific questions, an RFI should be submitted through Compass before end of bidding.  GC is also responsible to make sure SBUX vendors are installing their equipment per the plan.

Full plans, Bid Notes, LLWL, Specifications, Change Log Sample, other documentation are available on BOX: https://sbuxsd.box.com/s/ndje4l8xwazfbuitv548mewm2mbcela5

GC will be responsible for ensuring ALL permits, including health and retail operating (if needed) have been applied for and paid.  Costs will be reimbursed via work order contract upon request. Any assistance required from Starbucks for these should be requested from GC a minimum of 2 weeks in advance of “need”.

GC must supply a detailed proposed schedule and sub list at time of bid. GC will also be required to fill out the SDS (Store Delivery Schedule) including a ship to address for a warehouse as soon as possible but no more than 14 days of notification of award of project. Warehouse storage at GC cost including 4 weeks before start of project.

Please note in addition to plans and specifications GC is responsible for coordination with ALL Starbucks 3rd party vendors, including but not limited to, Sign Vendor (Hilton) Casework Vendor (JBI, DisplayIt), HME, CDW, NAVCO/Securitas, MELINK, Coolsys, Vixxo, ICEE, Kay Chemical, etc.  GC is accountable to inform vendors of any schedule shifts to avoid go-back fees.  If the vendors are not informed in a timely manner of a schedule shift and a go-back fee is incurred, the GC will be responsible to cover the cost.

GC is also responsible for the rollover of utilities from LL after Starbucks takes possession of the building at DOP. GC is responsible for utility costs during construction. GC must submit the utility meter submission form or email photos of meters to PS as soon as meters are installed.  A delay in submission of meters can cause a delay in transfer of utilities to SBUX responsibility.

Specifications for all Starbucks specified and provided items are available on Box see link:   STARBUCKS DESIGN CATALOG

GC is solely responsible for receipt of all SBUX provide materials and is solely responsible for delivery and receipt of all materials at the job site. GC should also plan to reference  SDRC GC Resources for additional information and requirements : SDRC - GC Resources GC, GC should be up to date on all conditions of the Master Services Agreement including punch list, warranty and completion requirements, and all requirements for supplying lien waivers and pay applications.

In addition, the following will be part of the contract:

Please note: the contractor must satisfy all Starbucks Coffee Company minimum standards and specifications all variances from approved plans should be verified thorough Starbucks Project Manager (PM) in writing. Daily reports from the field are required including Open Space captures every 3 days and should include at minimum, scope of work completed previous day, scope of work to be complete in the next 24 hours, status of all inspections, status of current work against actual schedule, copy of all outstanding questions or RFI’s, photos of work performed in previous 24 hours, change orders, etc. at that point in project.  Updates should be submitted to PM and PS and BOX email link daily before 9 am.

GC’s should also be familiar with the documentation in the Starbucks Store Development Resource Center (SDRC).  Here is a link: SDRC - GC Resources

See plans and LLWL in bid folder for additional comments.

for additional comments.